## Feedback tracker
Great job
1 | Color-code profit and loss numbers; red for less than zero, green for the rest. This is across all the screens.
2 | We need to refurbish the summary completely. For now, keep the summary as per below: (provide details from the email)
a. No combined view. It's not used widely.
b. Two vertical sections. One is for the longhorn and one for the endowment.
c. Each section to have following:
i) Current value (date to be mentioned)
ii) Return timeline - 1 day, 5 days, Mar'26TD, 3M, 6 across benchmark and respective portfolio. For benchmark, keep it blank for now, we'll deal with it later on how to calculate.
iii) For
3 | Holdings Tab
a. Export feature - only in CSV in the holding tabs across all three tables.
b. Dollar values in complete numbers and not in millions or thousands
c. Move the weight column to the right of mkt value
d. Can we have a snapshot of the past older holdings? While the real time is great, I also want teams to access older holdings - if no data is available, then just mention no data found. But I don't want prices to refresh for those. I want an exact end-of-day snapshot.
i) Remove all holdings tab completely
ii) Provide a summary below the search/load section. Summary to include date, portfolio value, cost, P&L%
iii) For this, let's provide a date field that the user can select. Calendar type field. Only one value to be accepted
iv) Default the value to the latest available date in the source holdings file for each of the portfolio
v) Add a date field in the grid as well. Fetch the value from the search section based on what the user has selected
vi) Either auto-refresh the table when the user selects a new date or give them a manual load button. If you are giving a manual, make sure to clear the table so the user knows that they have to click the load button
vii) If the data is available for the selected date, show it on the screen. For price/market value, first use the data available in the file, if not, fetch it from the yfinance.
viii) If the data is not available for the selected date, mention that the data is not available. Please select a date after 1st May 2026.
ix) Remove the daily P&L and Daily P&L %. Not very relevant
x) Is there a way to denote which sorting is in use (maybe highlight that field)
A new '2027 TMIA Trades' Screen - Reflection of our past trades
Make the URL Secure
Renaming
GIT Portfolio

## Milestone
Project: Portfolio Analytics Dashboard
Milestone 1 — Foundation & Data Layer
Goal: Get data flowing from local files into a working backend
# | Task | Details | Status
1.1 | Define data schema | Finalize columns for holdings, prices, benchmark, constraints files | In progress
Holdings (Data, Ticker, Name, GICS, Unit, Price, MV, Weight, Type)
1.2 | Create sample data templates | Excel/CSV templates with expected format
1.3 | Build data ingestion layer | Python module to read local Excel/CSV files, validate, and normalize
1.4 | Integrate live price feed | yfinance integration for real-time/delayed prices
1.5 | Build data refresh logic | Auto-reload when files change or on a timed interval
Deliverable: Data pipeline that reads local files and serves clean dataframes
Milestone 2 — Portfolio Analytics Engine
Goal: All calculations working and tested independently of any UI
# | Task | Details
2.1 | Portfolio return calculations | Daily, cumulative, annualized returns
2.2 | Risk metrics | Volatility, VaR (parametric + historical), max drawdown
2.3 | Benchmark-relative metrics | Beta, tracking error, information ratio, active share
2.4 | Risk-adjusted metrics | Sharpe ratio, Sortino ratio, Treynor ratio
2.5 | Breakdown calculations | Sector, geography, market cap, asset class weights
2.6 | Constraint checker | Engine that evaluates portfolio against user-defined rules
2.7 | Unit tests for analytics | Validate calculations against known results
Deliverable: Standalone Python analytics module with tested outputs
Milestone 3 — Dashboard UI (Local)
Goal: Interactive dashboard running on localhost
# | Task | Details
3.1 | Dashboard layout & navigation | Sidebar, tabs, overall page structure
3.2 | Holdings overview page | Positions table with P&L, sortable/filterable
3.3 | Breakdown views page | Sector, geography, market cap charts (Plotly)
3.4 | Analytics page | Risk metrics, benchmark comparison, return charts
3.5 | Constraint monitor page | Green/red flags, breach alerts, threshold gauges
3.6 | Summary/home page | Key KPIs, portfolio snapshot, top movers
3.7 | Interactivity | Date range selectors, drill-downs, hover tooltips
3.8 | Auto-refresh | Live reload of data at configurable intervals
Deliverable: Fully functional dashboard on localhost
Milestone 4 — Access Control & Security
Goal: Restrict access to authorized users only
# | Task | Details
4.1 | Authentication system | Login page with username/password
4.2 | User management | Add/remove users, role assignment (admin vs viewer)
4.3 | Session management | Token expiry, logout, session timeout
4.4 | Audit logging | Log who accessed what and when
Deliverable: Secured dashboard with login-gated access
Milestone 5 — Deployment & Multi-User Access
Goal: Make it accessible to fund managers beyond your local machine
# | Task | Details
5.1 | Decide hosting approach | Local network (LAN) vs VPS vs cloud VM
5.2 | Dockerize the application | Dockerfile + docker-compose for one-command setup
5.3 | Set up reverse proxy | Nginx with SSL (HTTPS)
5.4 | Deploy & configure firewall | Lock down to authorized IPs or VPN
5.5 | Set up domain (optional) | Custom domain or subdomain for easy access
5.6 | User acceptance testing | Fund managers test and provide feedback
Deliverable: Dashboard accessible to all authorized users securely
Milestone 6 — Polish & Enhancements
Goal: Production-quality experience
# | Task | Details
6.1 | Error handling & edge cases | Missing data, market holidays, stale prices
6.2 | Performance optimization | Caching, lazy loading for large datasets
6.3 | Export functionality | Download reports as PDF/Excel
6.4 | Alerts/notifications | Email or Slack alerts on constraint breaches
6.5 | Documentation | User guide for fund managers, setup guide for maintainers
Deliverable: Polished, production-ready dashboard
Suggested Execution Order
M1 (Foundation) → M2 (Analytics) → M3 (UI) → M4 (Auth) → M5 (Deploy) → M6 (Polish)
~2 days ~3 days ~4 days ~2 days ~2 days ~2 days
M1–M3 get you a working local dashboard (~9 days) M4–M5 make it accessible to others (~4 days) M6 is ongoing improvement
Want me to save this as a project plan file in your directory so you can track progress? And when you're ready to start, we can kick off Milestone 1 — I'd just need to see your data format (or we design one together).